## User Stories
USER STORIES - MediLink
Module | Title | As a/an | I want to... | So that I can... | Sprint | Story Points | Story Constraints | Story Exceptions
01. Account Management (Patient & Doctor) | 01.01 Sign-up User | Customers (Patients Requirements), Customers (Healthcare Providers requirements) | sign up for an account | access my health records and services | S1 | 4 | User is able to sign up but account activation email may be delayed | User may experience issues if they don't receive the activation email
| 01.02 log In User | Customers (Patients Requirements), Customers (Healthcare Providers requirements) | log into my account | manage my profile and view records | S1 | 4 | User may experience login issues due to incorrect credentials | User may forget their password and need to reset it
| 01.03 Modify Account | Customers (Patients Requirements), Customers (Healthcare Providers requirements), Sales Manager, Account Manager, Finance Manager | modify my account details | keep my information up-to-date | S1 | 4 | User may encounter errors when modifying account details | Changes may not be saved correctly due to server issues
| 01.04 Manage Subscription | Customers (Patients Requirements), Customers (Healthcare Providers requirements), Sales Manager, Account Manager | manage my subscription | adjust my plan as needed | TBD | 3
| 01.05 Delete Account | Customers (Patients Requirements), Customers (Healthcare Providers requirements) | delete my account | remove my information from the platform | S2 | 4 | User may encounter issues when attempting to delete their account | Account deletion may not be processed correctly
02. Record Search | 02.01 Search by Unique ID | Customers (Healthcare Providers requirements) | search for records by unique ID | quickly access my health information | S2 | 4 | User may encounter no results if the Unique ID is incorrect | User may face issues if the Unique ID is not found in the system
| 02.02 Search by Mobile Number | Customers (Healthcare Providers requirements) | search for records by mobile number | find patients easily | S2 | 4 | User may find no records if the mobile number is incorrect | User may input an invalid mobile number format
| 02.03 Search by Email | Customers (Healthcare Providers requirements) | search for records by email | access my health information | S2 | 4 | User may find no records if the email is incorrect | User may input an invalid email format
03. Health Records Management | 03.01 Create Record | Customers (Healthcare Providers requirements) | create a new health record | keep track of my medical history | S1 | 4 | User may encounter validation errors when creating a record | Patient record creation may fail due to system errors
| 03.02 Upload Report | Customers (Healthcare Providers requirements) | upload medical reports | maintain accurate health records | S1 | 4 | User may face issues with unsupported file formats | Report upload may fail due to large file size
| 03.03 Update Treatment Information | Customers (Healthcare Providers requirements) | update treatment info | provide accurate and timely care | S2 | 4 | User may encounter issues with validation errors | Treatment information updates may not be saved correctly
| 03.04 Manage Prescriptions | Customers (Healthcare Providers requirements) | manage my prescriptions | ensure I have the correct medications | S3 | 4 | User may face validation errors while updating prescriptions | Prescription updates may not be processed correctly
| 03.05 Email Notifications | Customers (Healthcare Providers requirements), Finance Manager | receive email notifications | stay informed about my records | S3 | 4 | Must opt-in to receive notifications | User may not receive timely updates
| 03.06 Manage Record | Customers (Healthcare Providers requirements) | manage my health records | keep my information organized | S3 | 4 | Must follow privacy regulations | User may encounter access issues
04. Finance Management | 04.01 Process Subscriptions | Customers (Patients Requirements), Customers (Healthcare Providers requirements) | process my subscription payments | maintain my subscription status | TBD | 3
| 04.02 Manage Billing & Payments | Customers (Patients Requirements), Customers (Healthcare Providers requirements) | manage my billing information | keep track of my payments | TBD | 3
| 04.03 Advertisement Performance and Report | Account Manager, Sales Manager | view ad performance reports | assess effectiveness of advertisements | TBD | 2
| 04.04 Generate Financial Reports | Finance Manager | generate financial reports | analyze my financial status | TBD | 3
05. Customer Support | 05.01 Payment Assist | Customers (Patients Requirements), Customers (Healthcare Providers requirements) | get assistance with payments | resolve any payment issues | TBD | 4
| 05.02 Track and Resolve Issues | Customers (Patients Requirements), Customers (Healthcare Providers requirements) | track my issues | ensure resolution of my concerns | TBD | 3
| 05.03 Feedback Forms | Customers (Patients Requirements), Customers (Healthcare Providers requirements) | submit feedback | help improve the platform | S3 | 4 | User may experience issues with feedback form submission | Feedback form responses may not be recorded accurately
| 05.04 Provide Quick Responses | Customers (Patients Requirements), Customers (Healthcare Providers requirements), Account Manager | receive quick responses | get timely answers to my queries | S3 | 3 | User may encounter issues with response quality | Responses may be delayed due to high query volume